## Bug Sheet_v_1.1
COMPUCOM TRACKER BUG SHEET
S.No. | Bug Id | Test Case Id | Bug Title | Defect Priority | Bug Description | Created By | Assign To | Current Status
1 | CSL_TRACKER_BUG_LIVE_TRACKING_B01 | CSL_TRACKER_LIVE_TRACKING_TC06 | Google API BUG | Low | Earth view of the google API not working | Swati | Amit | Unresolved
2 | CSL_TRACKER_BUG_DEVICE_REGISTERATION_B02 | CSL_TRACKER_DEVICE_EDIT_TC12 | Phone number length in Track Registeration page Bug | Medium | Mobile number input text box is allowing 15 digit mobile number. | Swati | Amit | Not a Bug as it is not allowing to save the 15 digit mobile number hence keeping our objective intact.
3 | CSL_TRACKER_BUG_DEVICE_REGISTERATION_B03 | CSL_TRACKER_MOBILE_NOTIFICATION_TC05 | Message pop up window position mismatch Dashboard Bug | Low | Position of the SMS message window for device records listed below the defined screen size are not appearing within the defined dimensions. | Swati | Amit | Unresolved
4 | CSL_TRACKER_BUG_DEVICE_REGISTERATION_B04 | CSL_TRACKER_TRIPREPORT_TC04 | Trip Report Bug | High | A complete Trip Report for the desired tracking devices is not appearing for the desired duration. | Swati | Amit | Resolved
5 | CSL_TRACKER_BUG_DASHBOARD_DISPLAY_B05 | CSL_TRACKER_USER_DASHBOARD_DISPLAY_TC01 | Dashboard UI Bug | Medium | Application name CSL GPS TRACKER is not appearing properly in the header section of Dashboard page | Swati | Amit | Resolved